## Slide 1: Project Vienna Diagnostic and Discovery Phase
Global Payments Europe
PwC
31. May 2026

## Slide 2: What? — Problem Statement Establishing a Fact-Based Operating Model View
Global Payments Europe currently operates a shared service center in Prague alongside multiple Joint Ventures (“JVs”) that perform services and processes locally. Over time, this has created a…
The key objective is to determine which services should be transitioned from the JVs to the shared service center, which existing JV capabilities could be scaled as best practice…
Client's Framework | PwC's Response
01 — WHAT is an SSC | ✅ Validated — we align to the GP SSC definition
02 — WHY do we need an SSC | ✅ Challenges mapped — our workstreams address each one
03 — BENEFITS for JVs & Enterprise | ✅ Benefits realization framework embedded in our approach
04 — TOM & Governance | ✅ Core of our proposal — RACI, Business Partnering, PMO, Intake
05 — The Road to SSCuccess | ✅ Detailed phased roadmap with timelines

## Slide 3: So What? — Opportunities During Discovery Key Focus Areas
Opportunity Area | Discovery Focus | 
Service & Process Transparency | Complete inventory across SSC, JVs and HQ | 
Reduce Duplication | Identify parallel execution across entities | 
JV Best Practices | Assess scalable mature capabilities in JVs | 
Service Placement Decisions | Criteria for local vs. central vs. scale-up | 
RACI & Governance | Clarify accountability between JVs, SSC and HQ | 
P&L & Cost Visibility | Baseline cost, headcount and allocations | 
Scalable JV Launch Model | Inputs for operational playbook and template | 

## Slide 4: Now What? Discovery Approach, Team and Timeline

## Slide 5: Discovery Approach Five Integrated Workstreams
WS1: Service & Process Mapping
Map services/processes across SSC, JVs and HQ.
WS1
WS5
WS2
WS3
WS4
WS2: RACI & Governance Mapping
Define roles; resolve ownership gaps and decision rights.
WS3: P&L, Cost & Headcount Review
Establish financial and workforce baseline.
WS5: Future-State Blueprint Inputs
Playbook, deployment template and transition roadmap.
WS4: Opportunity Assessment
Evaluate placement: local, SSC, JV scale-up or central build.
Discovery Phase
Client’s Transformation Step | PwC Interpretation
AS-IS: “Evaluate and map current end-to-end processes incl. all systems, services and (external) vendors” | Targeted fact-gathering only — we will extract data on SLAs, contracts, pricing, inputs, and vendor landscape without exhaustive process mapping
AS-IS: “Identify gaps, inefficiencies & duplications” | Capture through stakeholder interviews and data analysis — embedded within each workstream, not a separate phase
AS-IS: “Assess cost base, existing (frame) contracts, SLAs and performance KPIs” | Core input to WS6 (Transfer Pricing) and cross-cutting Fact Base
AS-IS: “Assess R&R, and ownership gaps” | Core input to WS1 (RACI)
TO-BE: “Define and agree SSC scope” | WS1 kick-off activity
TO-BE: “Design TOM – customer oriented service delivery model” | WS1 + WS2 + WS3 combined
TO-BE: “Establish governance, roles & accountability” | WS1: RACI & Governance Charter
TO-BE: “Review & build Frame Agreements, Product & Service Catalogue” | Cross-cutting deliverable + WS6
TO-BE: “Set-up/Update intercompany charging model” | WS6: Transfer Pricing
TO-BE: “Identify quick wins” | Each workstream identifies quick wins in Phase 1
TO-BE: “Define & approve Roadmap phasing & prioritization” | WS2: PMO; overall roadmap in Slide 18

## Slide 6: Tentative Timeline 8–16 Week Diagnostic Program
Wk 15-16
Wk 11-14
Wk 7-10
Wk 3-6
Wk 1-2
Mobilization and Data Request
Confirm scope, JVs in scope, governance, templates, stakeholders, and data requirements.
Current-State Discovery
Conduct interviews and workshops; map services, processes, systems, ownership, volumes, and…
Analysis and Opportunity Identification
Identify duplication, fragmentation, best practices, cost drivers, and service placement…
Future-State Options and Prioritization
Prioritize transition candidates, define future-state RACI, and agree initial operating model…
Findings and Next-Phase Handover
Finalize diagnostic findings, opportunity backlog, roadmap, and inputs for the operational…

## Slide 7: Required Project Team
Project Lead / PM
Delivery plan, governance and reporting
Finance / FP&A Lead
P&L, cost allocation and business case
SSC Operations Lead
Prague SSC capabilities, capacity and constraints
Executive Sponsor
Strategic direction and priority confirmation
Process Excellence Lead
Process mapping and opportunity prioritization

## Slide 8: Expected Outputs End-of-Discovery Deliverables
Key Deliverables
  • Service and process inventory (SSC, JVs, HQ)
  • Process maps for priority services
  • RACI matrix and decision rights
  • P&L, cost and headcount baseline
Analysis & Recommendations
  • Duplication and fragmentation analysis
  • JV best-practice scale-up assessment
  • Service placement recommendations
  • Playbook and deployment template inputs

## Slide 9: Industry Standards & Methodologies Structured Discovery Techniques
Lean Six Sigma
Waste, rework and variation diagnostics.
SIPOC & Process Maps
End-to-end boundaries, handoffs and controls.
Service Catalogue
APQC-aligned taxonomy for like-for-like comparison.
RACI / RAPID
Workshop-based role and decision-rights clarity.
03
02
01
04
GBS Maturity Lens
Standardization, automation, KPIs and scalability.
05

## Slide 10: GBS Maturity & Benchmarking Comparison to Leading Practice
Dimension | GP Current State | GP To-Be (with PwC) | Industry Leading Practice | Standard / Source
Governance | Fragmented; no formal RACI; disjointed goals across locations | 3D RACI across PDLC / SSC Ops / Customer; quarterly Governance Forum; decision rights at 3 levels | Living RACI integrated with HRIS & org charts; automated alerts on role changes | COBIT 2019; ITIL 4
Intake & Ticketing | Unstructured; email/phone/personal contacts | Unified portal; auto-classification; SLA clock; real-time dashboard | AI-assisted triage; self-service portal with chatbot first line; predictive routing | ITIL 4 Service Desk; HDI
SLA Management | Informal; inconsistent; unmeasured | Defined SLAs per service × customer; tracked in case management; escalation engine | Tiered SLAs (Bronze/Silver/Gold); automated penalty/credit; SLA-linked commercial incentives | SSON Benchmarks; Gartner GBS
PMO & Portfolio Steering | None | Centralized PMO; intake gating; portfolio dashboard; prioritization scoring | Enterprise PMO with OKR integration; capacity planning; benefits tracking; demand forecasting | PMI PMBOK 7th Ed; SAFe
Post-Acquisition Integration | Unstructured workarounds | A?B?C?D framework; workaround register; bridge state SOPs; readiness checklists | Integration playbooks; Day 1/30/60/90 milestones; automated parallel-run reconciliation | PMI M&A Integration; DORA
Continuous Improvement | Limited | Improvement loops fed by benchmarking, post-acquisition lessons and KPI trend analysis | Lean Six Sigma embedded in GBS; Kaizen events; digital twin simulation of process changes | Lean Six Sigma; Hackett
Standardization • Centralization • Automation • KPIs • Controls • Scalability

## Slide 11: RACI & Operating Model Design Roles Across JVs, SSC and HQ
Responsible
Who performs the activity
Accountable
Who owns the outcome and decision
Consulted
Who provides input before action
Informed
Who is updated after the decision
Dimension | What It Covers | Example
People | Roles, reporting lines (direct & dotted) across Prague, Poland, Spain; PDLC (Products & Tech), SSC Operations, SSC RM for JVs, Customer/JV | Who is Responsible for KYC onboarding in Prague vs. who is Accountable in the JV business unit?
Process | End-to-end service delivery processes (KYC, Fraud Investigation & Prevention, Dispute Management, Risk Monitoring, Tech Development) | Who is Consulted when a dispute SLA is breached? Who is Informed?
Technology | System ownership, data stewardship, platform decisions, automation roadmap | Who is Accountable for the fraud detection platform roadmap within PDLC (Products & Tech)?

## Slide 12: SIPOC & Process Mapping From Documentation to Simplification
SIPOC maps Suppliers, Inputs, Process, Outputs and Customers. Detailed flowcharts capture handoffs, controls, rework and system touchpoints — revealing duplication before transition.
Addressing complexity across JVs, SSC and HQ
Simplify before transition
Identify duplication and gaps
Map handoffs and decision points
Define process boundaries (SIPOC)
Validate with process owners
04
03
02
01
05
PwC
Deliverable | Description | Linked to Client’s TOM
Master RACI Matrix | Interactive digital artifact (SharePoint/Confluence) covering People × Process × Technology for all Prague SSC services across PDLC, SSC Ops, SSC RM, and Customer/JV groups | Pillar 1: Clear Structure
RACI Heat Map | Visual overlay showing concentration of Accountability — identifying single points of failure or over-centralized decision-making | Pillar 1
Governance Charter | Rules of engagement: decision rights at strategic/tactical/operational levels; escalation protocols; cadence of review (quarterly recommended) | Governance Framework
KPI Ownership Map | Each KPI (service availability, processing quality, as referenced by the client) assigned to a single “A” owner | Pillar 4: Commercial Transparency & Performance
RACI Change Procedure | Formal process for updating RACI when new services, acquisitions, or org changes occur — gated through PMO (WS2) | Pillar 5: Continuous Improvement

## Slide 13: Service Placement Options Four Future-State Paths
A. Remain Local
Regulatory, language or proximity requires JV delivery.
B. Transition to SSC
Standardizable processes for Prague SSC.
C. Scale JV Capability
Reuse mature JV service across entities.
D. Build Central Capability
New scalable solution required.

## Slide 14: Thank you
© 2026 PricewaterhouseCoopers. All rights reserved.
Strictly confidential — non-binding discovery overview.