## Slide 1: Global Payments Shared Service Center Transformation
PwC Slovakia
22. April 2026

## Slide 2
Dagmar Haklová
Partner
PricewaterhouseCoopers Tax, k.s.
Bratislava
T: +421 259 350 111
www.pwc.com/sk
Dear Mrs. Rohrhofer,
Thank you for the opportunity to discuss the transformation of Global Payments' Prague Shared Service Center. Your SSC Concept — "From Silo to Service Excellence" — provides a compelling vision, and our proposal is built directly on your blueprint .
PwC will operationalize your Target Operating Model through six integrated workstreams: RACI & Governance, Business Partnering & PMO, Intake & Case Management, Post-Acquisition Transition, Subcontractor Governance, and Transfer Pricing — each mapped to your TOM pillars and the challenges you have identified . At the core sits a three-dimensional RACI framework across your structural groups (PDLC, SSC Ops & RM, Customer/JV), sustained through a Governance Forum, Business Partners, and a PMO gating every new initiative . Alongside, we help design the fact base — SLA dashboards, pricing catalogue, dispute analytics — enabling the evidence-based customer conversations needed to earn trust and attract new workloads to Prague.
We look forward to starting the road to SSCuccess together — "turning complexity into a competitive advantage for the whole group" .
Yours sincerely,
Dagmar Haklová
Tomáš Kubányi
Director
PricewaterhouseCoopers Tax, k.s.
Bratislava
T: +421 904 233 423
www.pwc.com/sk

## Slide 3: Vision — We Heard You PwC's Proposal Is Built on Your Own Blueprint
This proposal directly responds to the SSC Concept by Global Payments. The client's vision, defines the SSC as a "centralized organizational unit/own entity providing services across multiple entities" that "operates as an internal service provider with defined services and performance levels" and "evolves into a centre of excellence over time."
PwC's Role: We are here to operationalize this vision — to take the "what" and "why" and deliver the "how" through structured workstreams, proven methodologies, industry benchmarks, and hands-on implementation support.
Client's Framework | PwC's Response
01 — WHAT is an SSC | ✅ Validated — we align to the GP SSC definition
02 — WHY do we need an SSC | ✅ Challenges mapped — our workstreams address each one
03 — BENEFITS for JVs & Enterprise | ✅ Benefits realization framework embedded in our approach
04 — TOM & Governance | ✅ Core of our proposal — RACI, Business Partnering, PMO, Intake
05 — The Road to SSCuccess | ✅ Detailed phased roadmap with timelines

## Slide 4: The Combined Governance Model — How It All Fits Together An Integrated Operating Model — "ONE Organization Delivering Services Efficiently for MANY"
Governance Forum
(Quarterly; SSC Head + PDLC Leads + JV/Enterprise Leads)
Reviews: RACI | KPIs | Portfolio | Escalations | Benchmarks
Business Partners (Dedicated Relationship Management)
PMO (Portfolio Steering)
Vendor Management Office
Unified Intake & Case Management
(ServiceNow or equivalent)
Disputes | Incidents | Projects | Workarounds
Master RACI Matrix
PDLC (Product & Tech) x SSC Ops/RM x Customer/JV
People x Process x Technology
(Living artifact; quarterly review; PMO-gated)
SLA & KPI Dashboard (Service availability, Processing quality)
Transfer pricing cube (Volume & Activity based)
Subcontractor scorecard
Key Message: This model delivers all five pillars of Global Payments TOM simultaneously. The RACI is the backbone; the intake system is the nervous system; Business Partners are the customer interface; the PMO is the brain; reporting and benchmarking are the eyes.

## Slide 5: From Today's Challenges to Tomorrow's Targets — Aligned View
TODAY (Client's Definition) | TARGET (Client’s Definition) | PwC Workstream
Unstructured INTAKE | Structured demand intake & prioritization | WS3: Intake Mechanism & Case Management
Limited transparency in prioritization | Transparent, centralized portfolio steering | WS2: PMO Function Design
Unclear operating model and accountability | Clear operating model and defined ownership | WS1: RACI Matrix & Governance Model
Inconsistent transfer pricing & intercompany set up | Standardized commercial framework (pricing & agreements) | WS6: Transfer Pricing Mechanism
Fragmented product ownership and strategy alignment | Standardized processes and clear end-to-end accountability | WS1 + WS2: RACI + Business Partnering
(Implied) Post-acquisition workarounds | Strong governance and performance management | WS4: Post-Acquisition Transition Framework
(Implied) Subcontractor inconsistency | Customer-oriented service delivery model | WS5: Subcontractor Governance Model

## Slide 6: Benefits Realization: JV Customers & Enterprise Making the Benefits Tangible and Measurable
For the CUSTOMER (JVs)
Higher service quality & reliability (SLAs)
Faster time-to-market
Clear transparency on services and costs
Ability to focus on clients and growth
PwC Enabler
WS1: RACI clarity → right owner, right response; WS3: Intake with SLA clock
WS2: PMO intake gating + portfolio prioritization; WS4: Structured acquisition integration
WS6: Pricing catalogue; WS cross-cutting: SLA/Pricing dashboard
WS2: Business Partnering takes the complexity away from JVs
Measurement
SLA attainment rate (target: >95%)
Average time from request to delivery (target: 30% reduction in 12 months)
Customer satisfaction score; pricing dispute reduction
NPS from JV customers
For the ENTERPRISE
Sustainable cost efficiency and scalability
Stronger governance & control
Full transparency on costs and performance
Standardization and reduced complexity
Platform for scalable growth and innovation
PwC Enabler
WS6: TP model; WS5: Subcontractor governance; WS3: Automated intake
WS1: RACI; WS governance forum; WS2: PMO
Cross-cutting: Real-time dashboards (Power BI)
WS1: Process RACI; WS3: Single intake portal
WS4: A→B→C→D framework; WS2: PMO capacity planning
Measurement
Cost per transaction; cost-to-serve ratio
Governance maturity score (PwC assessment)
Dashboard adoption; data accuracy rate
Process variation index; number of workarounds active
New workloads onboarded per quarter

## Slide 7: PwC Capabilities Matching Your target operating model (TOM) Your Target Operating Model — Our Proven Capabilities
Customer-Provider Model — How Teams Interact:
Client’s description: Demand intake & prioritization; Capacity & resource allocation; Regular service reviews & feedback loops; Dedicated Relationship Management
Business Partnering Design — Deployed at 50+ GBS centers; PMO Design; ServiceNow/Salesforce implementation for intake and case management.
Service Delivery — How Services Are Delivered:
Client’s description: Standardized & defined processes; Defined Product & Service Catalogue
Process Excellence & GBS Advisory — 20+ years designing service catalogues and standardizing SSC processes; proprietary database of 1,600+ SSC benchmarks.
Clear Structure — Who Does What:
Client’s description: PDLC (Products & Tech); SSC Operations & SSC RM for JVs; Customer/JV
Operating Model Effectiveness (OME) — PwC's proprietary framework for designing roles, decision rights, and reporting structures across complex multi-entity organizations. Org Design practice.
Commercial Transparency & Performance:
Client’s description: Transparent intercompany charging; Pricing based on volumes & activities; Clear cost allocation; KPI-driven performance (service availability, processing quality)
Transfer Pricing Advisory (#1 globally, International Tax Review); Performance Management & Dashboarding (Power BI/Tableau).
03
02
01
04
Technology & Continuous Improvement:
Client’s description: Standardization (limit customization); Automation & STP processing first approach; Design for growth, quality and speed; Continuous improvement loops; Benchmarking
Intelligent Automation (RPA, AI); Technology Strategy; Benchmarking & Continuous Improvement frameworks aligned to Lean Six Sigma and ITIL 4.
05

## Slide 8: Industry Benchmarking & Standards Comparison How Does the To-Be Model Compare to Industry Leaders?
Dimension | GP Current State | GP To-Be (with PwC) | Industry Leading Practice | Standard / Source
Governance | Fragmented; no formal RACI; disjointed goals across locations | 3D RACI across PDLC / SSC Ops / Customer; quarterly Governance Forum; decision rights at 3 levels | Living RACI integrated with HRIS & org charts; automated alerts on role changes | COBIT 2019; ITIL 4
Intake & Ticketing | Unstructured; email/phone/personal contacts | Unified portal; auto-classification; SLA clock; real-time dashboard | AI-assisted triage; self-service portal with chatbot first line; predictive routing | ITIL 4 Service Desk; HDI
SLA Management | Informal; inconsistent; unmeasured | Defined SLAs per service × customer; tracked in case management; escalation engine | Tiered SLAs (Bronze/Silver/Gold); automated penalty/credit; SLA-linked commercial incentives | SSON Benchmarks; Gartner GBS
PMO & Portfolio Steering | None | Centralized PMO; intake gating; portfolio dashboard; prioritization scoring | Enterprise PMO with OKR integration; capacity planning; benefits tracking; demand forecasting | PMI PMBOK 7th Ed; SAFe
Post-Acquisition Integration | Unstructured workarounds | A?B?C?D framework; workaround register; bridge state SOPs; readiness checklists | Integration playbooks; Day 1/30/60/90 milestones; automated parallel-run reconciliation | PMI M&A Integration; DORA
Continuous Improvement | Limited | Improvement loops fed by benchmarking, post-acquisition lessons and KPI trend analysis | Lean Six Sigma embedded in GBS; Kaizen events; digital twin simulation of process changes | Lean Six Sigma; Hackett
Benchmarking across entities and market competition

## Slide 9: Tentative Timeline — The Road to "SSCuccess"
Wk 22- 25
Wk 18-21
Wk 10-17
Wk 4-9
Wk 1-3
Phase 1: Targeted Discovery & Design Sprint
  WS1, WS2, WS3, WS6 + Fact Base; Service catalogue v1.0; RACI v1.0 drafted across PDLC / SSC Ops / Customer/JV; intake system requirements; TP policy options; SLA/pricing/dispute fact base v1.0; quick wins identified per workstream
Phase 3: Pilot & Iterate
  WS1, WS2, WS3, WS4; RACI published to all stakeholders; BP pilot with 1–2 JV customer groups; intake system pilot (1 service line); first Governance Forum conducted; A→B→C→D tested on real acquisition case
Phase 0: Mobilization
  All workstreams; Project kickoff; data requests issued; stakeholder mapping; interview scheduling; alignment on SSC scope (client's TO-BE step 1)
Phase 2: Detailed Design & Build
  All workstreams; RACI v2.0 validated in workshops; BP role profiles & JDs; PMO charter & prioritization framework; intake system sandbox configured; A→B→C→D framework documented; subcontractor governance framework; TP model built; Frame Agreements reviewed
Phase 4: Embed & Handover
  All workstreams; Full rollout plan; training delivered; dashboards live; TP reporting operational; PwC handover documentation; sustainability plan; Roadmap phasing & prioritization approved (TO-BE final step)

## Slide 10: Why PwC team
Engagement partner
Overall relationship; quality assurance; executive access
RACI & Governance Lead
Manager, Org Design
Experience in process mapping, optimization and improvement
Experienced in local and global accounting standards, SSC setup & evolution, as well as Tax, Risk & Regulation and compliance topics
Bringing efficiencies through automations and process improvements to our clients
Strong experience in various accounting systems and workflows
Experience with process onboarding, optimisation and process standardization, especially in Shared Services
End to end expertise in process insourcing and outsourcing
Experience with transfer pricing
Project Director
Day-to-day leadership; workstream coordination
Director, Operating Model & Governance; 20+ years in multi-country SSC experience
Change & Comms Lead
Manager, Change Management; GBS transformation experience

## Slide 11: References
Selected accounting and tax compliance projects
Large online retail company – SSC O2C and P2P model setup
Setting up and continuously improving the AR, AP, CashApp, Billing and Treasury services
Cloud services provider – legal entity setup
Setting up billing and customer relationship service operation for EMEA region.
PwC CEE IFS SSC Bratislava Managed Services
Managed services for 15 countries in the PwC network
Finance functions O2C, P2P, R2R, Project management, Data quality​
Information Technology​
Personal assistance​
Risk Management​, MCBD​, Human Capital
Savencia Process Improvement & Audit Project Management
Implementation of Lean principles to foster a culture of continuous improvement
Efficiency and performance enhancement through innovative workflows and full utilization of individual potential
Interim project management with expertise in SSC audit processes and communication with external auditors
Cetin Networks Finance Business Process Outsourcing
Providing key strategic financial and accounting services
Acting as an SSC for the client
Supporting all transactional process within P2P, C2C and R2R​
Assistance on IFRS 16 process​
SAP update supervision​

## Slide 12: Pricing Structure

## Slide 13: Pricing
Bringing clarity, accountability, and scale into one entity, we turn complexity into a competitive advantage for the whole group. Global Payments SSC Vision
PwC is ready to make this vision operational.
The timeline spans 25 weeks and assumes 110 days of engagement for, including Project Director, RACI & Governance lead 3 PwC staff members (manager level) and Change & comms lead (senior associate level).
The PwC fee is calculated at EUR 79,960
“

## Slide 14: Fees & cost structure
The pricing calculation assumes timely cooperation with Global Payments leadership and staff allowing to meet the timelines for “as-is” mapping, as well as “to-be” state review and approvals
Access to Global Payments systems is considered highly restricted thus data and information needs to be sourced by PwC staff through Global Payments employees
    All fees are in EUR, excluding VAT.
Out-of-pocket expenses, such as travel costs, couriers and fees payable to supervisory authorities, will be charged at cost.
Our fees are based on the assumption, that we will receive high quality data in a pre agreed format and in accordance with pre agreed timetables.
Fees are estimated for core services. We are happy to estimate fixed fee quotes for other optional and additional services or provide them on based on our hourly rates.
Assumptions and staffing definitions

## Slide 15: Thank you
© 2026 PricewaterhouseCoopers. All rights reserved. In this document, “PwC” refers to the PwC network and/or one or more of its member firms, each of which is a separate legal entity. ​
​
This document is not a contract and please consider its content as strictly confidential. Further, please note that the provision of our services is subject to the Company's verification from the risk management and auditor independence perspective, as well as to the signing of an engagement letter for the provision of services. Thus, before we finalise all risk management steps, please consider this to be a non-binding proposal.

## Slide 16: Our Approach: Six Integrated Workstreams
RACI Matrix & Governance Model
(TOM Pillar 1 & Gov)
WS6
WS2
WS3
WS5
WS1
WS4
Workstream architecture
Business Partnering & PMO
(TOM Pillar 3)
Intake Mechanism & Case Mgmt
(TOM Pillar 3)
Post-Acquisition Transition
(TOM Pillar 5)
Subcontractor Governance
(TOM Pillar 2)
Transfer Pricing & Reporting
(TOM Pillar 4)
Cross Cutting
Guiding principle
"AS-IS Assessment" and "2. Define TO-BE" . PwC honours the client's stated preference to focus on the TO-BE, while conducting a targeted, lightweight AS-IS only where necessary to build the fact base (SLAs, pricing, disputes, cost base)
SLA / Pricing / Dispute Fact Base
Product & Service Catalogue
Benchmarking & Continuous Improvement
Change Management & Comms
Client’s Transformation Step | PwC Interpretation
AS-IS: “Evaluate and map current end-to-end processes incl. all systems, services and (external) vendors” | Targeted fact-gathering only — we will extract data on SLAs, contracts, pricing, inputs, and vendor landscape without exhaustive process mapping
AS-IS: “Identify gaps, inefficiencies & duplications” | Capture through stakeholder interviews and data analysis — embedded within each workstream, not a separate phase
AS-IS: “Assess cost base, existing (frame) contracts, SLAs and performance KPIs” | Core input to WS6 (Transfer Pricing) and cross-cutting Fact Base
AS-IS: “Assess R&R, and ownership gaps” | Core input to WS1 (RACI)
TO-BE: “Define and agree SSC scope” | WS1 kick-off activity
TO-BE: “Design TOM – customer oriented service delivery model” | WS1 + WS2 + WS3 combined
TO-BE: “Establish governance, roles & accountability” | WS1: RACI & Governance Charter
TO-BE: “Review & build Frame Agreements, Product & Service Catalogue” | Cross-cutting deliverable + WS6
TO-BE: “Set-up/Update intercompany charging model” | WS6: Transfer Pricing
TO-BE: “Identify quick wins” | Each workstream identifies quick wins in Phase 1
TO-BE: “Define & approve Roadmap phasing & prioritization” | WS2: PMO; overall roadmap in Slide 18

## Slide 17: Workstream 1: RACI Matrix & Governance Model (1/2) The Backbone — "Who Decides & Who Is Accountable"
"Who owns decisions (decision rights — strategic, tactical, operational)“
Decision Rights Matrix — maps strategic decisions (e.g., new product launch) to Enterprise leadership; tactical decisions (e.g., SLA target-setting) to SSC Head + Business Partners; operational decisions (e.g., daily case routing) to team leads per RACI
"How priorities are set (portfolio steering)“
Portfolio Steering Committee design — membership, cadence (monthly), scoring model for prioritization — linked to WS2 PMO
"How performance is monitored (KPIs, SLAs)“
KPI Ownership Map — each KPI assigned a single "A" (Accountable) owner; dashboard design (see WS cross-cutting)
"How conflicts are resolved (escalation paths)“
Escalation Protocol — 3-tier escalation: L1 (operational — team lead, 24h), L2 (tactical — Business Partner, 48h), L3 (strategic — Governance Forum, 5 days)
The three structural groups the client identifies — PDLC (Products & Tech), SSC Operations & SSC RM for JVs, and Customer/JV — become the three axes of our RACI design. Every service, process, and technology decision is mapped across these three groups.
Dimension | What It Covers | Example
People | Roles, reporting lines (direct & dotted) across Prague, Poland, Spain; PDLC (Products & Tech), SSC Operations, SSC RM for JVs, Customer/JV | Who is Responsible for KYC onboarding in Prague vs. who is Accountable in the JV business unit?
Process | End-to-end service delivery processes (KYC, Fraud Investigation & Prevention, Dispute Management, Risk Monitoring, Tech Development) | Who is Consulted when a dispute SLA is breached? Who is Informed?
Technology | System ownership, data stewardship, platform decisions, automation roadmap | Who is Accountable for the fraud detection platform roadmap within PDLC (Products & Tech)?
PwC’s 3D RACI Methodology

## Slide 18: Workstream 1: RACI Matrix & Governance Model (2/2) Making RACI Operational — Not Shelfware
Dual-Axis RACI — For each process/service, the RACI explicitly shows both the functional accountability (Prague SSC) and business line accountability (country/product group)
Conflict Resolution Protocol — Where RACI reveals two groups claiming "A", PwC facilitates resolution workshops with a structured decision framework
Business Partner as Alignment Broker (WS2) — BPs serve as the ongoing mechanism to keep direct and dotted-line stakeholders aligned
Governance Forum — Quarterly session where RACI conflicts are surfaced and resolved at leadership level
Addressing the Direct vs. Dotted-Line Complexity
The Prague SSC has people with direct reporting lines to Prague leadership and dotted lines to other countries and locations (& vice versa). PwC addresses this through:
Straight-Through Processing (STP)
End-to-end automation for PO-backed invoices
Exception-Based Processing
Human intervention only for outliers
Three-Way Matching Automation
PO, Receipt, Invoice matching
Centralized intake
Single point of invoice submission replacing multiple email addresses
Continuous Vendor Management
Proactive communication & relationship building
04
03
02
01
05
PwC
Deliverable | Description | Linked to Client’s TOM
Master RACI Matrix | Interactive digital artifact (SharePoint/Confluence) covering People × Process × Technology for all Prague SSC services across PDLC, SSC Ops, SSC RM, and Customer/JV groups | Pillar 1: Clear Structure
RACI Heat Map | Visual overlay showing concentration of Accountability — identifying single points of failure or over-centralized decision-making | Pillar 1
Governance Charter | Rules of engagement: decision rights at strategic/tactical/operational levels; escalation protocols; cadence of review (quarterly recommended) | Governance Framework
KPI Ownership Map | Each KPI (service availability, processing quality, as referenced by the client) assigned to a single “A” owner | Pillar 4: Commercial Transparency & Performance
RACI Change Procedure | Formal process for updating RACI when new services, acquisitions, or org changes occur — gated through PMO (WS2) | Pillar 5: Continuous Improvement

## Slide 19: Workstream 2: Business Partnering & PMO Function Design (1/2) The Connective Tissue — Dedicated Relationship Management & Portfolio Steering
Role Definition
  Business Partners are translators, aligners, and relationship managers — NOT doers. They represent the Prague SSC to JV/Enterprise customers and represent customer needs back to the SSC
Scope
  Each BP covers a defined portfolio of customers (JVs and/or Enterprises) and a mapped set of services from the Product & Service Catalogue
Key Activities
Quarterly RACI alignment sessions; SLA performance reviews with customers; demand management and intake facilitation; dispute facilitation; new workload onboarding; regular service reviews & feedback loops (as specified by the client
Reporting
  Reports to Prague SSC Head; dotted line to relevant business/product group leads (mirrors the structure it governs)
KPIs
  Customer satisfaction (NPS), workload migration success rate, SLA attainment, dispute resolution time, new competency onboarding rate
Interface Role
  BPs play the critical interface between Prague SSC and PDLC (Products & Tech), SSC Operations, and Customer/JV groups — regularly aligning the RACI matrices
Role Definition
Scope
Interface Role
Reporting
Key Activities
KPIs
A. Business Partnering Function

## Slide 20: Workstream 2: Business Partnering & PMO Function Design (1/2) The Connective Tissue — Dedicated Relationship Management & Portfolio Steering
Intake Gate
  Every new initiative (project, product, acquisition workaround, customer request) must pass through a PMO intake gate — RACI impact assessed, resources allocated, SLA defined
Prioritization Framework
  Weighted scoring model (strategic alignment with SSC vision, customer impact, resource/capacity availability, risk, time-to-value) — directly addressing the client's call for "transparent, centralized portfolio steering"
Capacity & Resource Allocation
PMO manages resource allocation across workloads — as specified in the client's TOM Pillar 3
Portfolio Dashboard
  Real-time consolidated view of all active projects, their RACI owners, status, and resource consumption
Cadence
  Weekly PMO stand-ups; monthly portfolio reviews with leadership; quarterly alignment with Governance Forum
Quick Wins Tracking
PMO maintains a dedicated quick-wins register — the client's transformation approach calls for "Identify quick wins" and the PMO ensures these are tracked to completion
Intake Gate
Prioritization Framework
Quick Wins Tracking
Portfolio Dashboard
Capacity & Resource Allocation
Cadence
B. PMO Function

## Slide 21: Workstream 3: Intake Mechanism & Case Management From "Unstructured INTAKE" to a Single Front Door
Single intake portal
Triage & classification engine
Assignment and SLA clock start
Autoroute by category: dispute, incident, project, acquisition workaround
RACI-based assignment; SLA per category; real-time dashboard
Web form, API, email to ticket
PwC Recommendation: ServiceNow CSM + ITSM — unified intake for both business and technology requests, with native SLA management, real-time reporting, and integration capability to feed the KPI dashboards that the client's TOM Pillar 4 demands. Alternatively PwC can build an intake and workflow management software on demand.
Platform | Strengths | Fit for GP
ServiceNow CSM + ITSM | Market leader; strong multi-category intake; enterprise-grade SLA engine | High
Salesforce Service Cloud | Strong CRM-native case management; customer-facing portal | Medium
Jira Service Management | Agile-friendly; good for tech dev intake | Medium — supplement for PDLC
BMC Helix (Remedy) | Legacy ITSM; strong in financial services | Medium — if existing footprint
Technology options
Principle | Implementation | Client TOM Alignment
Single Front Door | All requests enter through ONE portal — no “I know someone” routing | Demand intake & prioritization
Auto-Classification | Rules-based + ML-assisted categorization (Dispute / Incident / Project / Acquisition / Workaround / Other) | Structured demand intake
SLA by Category | Each category has defined response and resolution SLAs, benchmarked to industry | Higher service quality & reliability (SLAs)
RACI-Based Routing | System auto-assigns to the correct Responsible owner based on the Master RACI Matrix | Clear operating model and defined ownership
Real-Time Dashboard | Live reporting: open/closed/aging tickets, SLA compliance %, category distribution, customer-specific views | Full transparency on costs and performance
Escalation Engine | Automated escalation when SLA thresholds are breached (80% ? notify; 100% ? escalate to Accountable owner per RACI) | How conflicts are resolved (escalation paths)
Key design principles

## Slide 22: Workstream 4: Post-Acquisition Transition Framework Structured Workarounds — Design for Growth, Quality and Speed
A. Acquisition Close
PMO registers "Acquisition Integration Project"; initial RACI impact assessment
B. Structured Workaround
Business Partner monitors; weekly status to PMO; workaround logged in intake system
C. Tech-Enabled Transition
PMO tracks milestones; PDLC (Products & Tech) owns delivery; RACI updated for new system role
D. Steady State
Business Partner conducts post-integration review; RACI finalized; KPIs baselined
As Global Payments makes acquisitions, human-operated workarounds bridge the gap until technology is adjusted. PwC structures this bridge with a clear A→B→C→D framework:
Key deliverables
Workaround Register Template — standardized log (process, owner, risk rating, target decommission date)
Bridge State SOP Template — reusable, with embedded controls
Transition Readiness Checklist — criteria for moving B→C and C→D
Risk & Control Matrix — compensating controls for each active workaround
Alignment to Client's Continuous Improvement Pillar: Each completed A→D cycle feeds into the "Continuous improvement loops" and "Benchmarking across entities" the client envisions — lessons learned are captured and applied to the next acquisition.
Human-operated processes with formal SOPs, interim SLAs, manual controls, reconciliation checkpoints
Day 1 post-close; acquired entity on legacy systems
Systems configured/integrated; parallel run (workaround + system); outputs reconciled
Full tech integration; workaround decommissioned; BAU operations

## Slide 23: Workstream 5: Subcontractor Governance Model Extending the GP Model — Consistent Quality Across the Ecosystem
1. Onboarding
Subcontractor Qualification Standard
  Minimum requirements: compliance certifications, process maturity, tech compatibility, PCI-DSS.
2. Contractual
GP Model Alignment Clauses
  Standard terms requiring adherence to GP's standardized processes (TOM Pillar 2) , SLAs, reporting formats, quality standards
3. Operational
Process Conformance Reviews
  Quarterly reviews; transaction sampling; mystery shopping; aligned to GP's "Standardization (limit customization)" principle
4. Performance
Subcontractor Scorecard
  Monthly KPIs: SLA compliance, error rates, customer complaints — feeding into the same KPI-driven performance framework (TOM Pillar 4)
5. Escalation
Non-Conformance Management
  Warning → corrective action plan → probation → termination
6. Integration
Unified Intake Access
  Subcontractors use the same intake/ticketing system (WS3) — unified visibility
Recommendation: Establish a lightweight Vendor Management Office (VMO) within the Prague SSC — 1–2 FTEs responsible for subcontractor onboarding, scorecard management, and conformance reviews.

## Slide 24: Workstream 6: Transfer Pricing Mechanism & Reporting Commercial Transparency — "Clear Cost Allocation and Visibility"
Component
€0.XX per payment processed
Per-transaction fee (volume-based)
Transaction processing
€XX per KYC review completed
Per-case fee (activity-based)
KYC / Fraud investigation
€XX per development hour
Time & materials (activity-based)
Tech development / changes
Base fee + per-incident charge
Monthly retainer (fixed + variable)
Ongoing support / monitoring
Subcontractor + X% GP mgmt fee
Cost plus markup
Subcontractor pass-through
Pricing method
Example
PwC’s Approach
Step | Activity | Output | Client TOM Link
1. Service Decomposition | Break each customer solution into component services; map to delivering entity (Prague SSC, other GP entity, subcontractor) | Service Component Map | Product & Service Catalogue
2. Cost Driver Analysis | Identify direct costs (FTE, technology, licenses) and indirect costs (overhead, management) per component | Cost Driver Model | Clear cost allocation
3. Pricing Model Design | Design intercompany pricing: Volume-based (per transaction) + Activity-based (per support hour, per change request) — exactly as the client specifies | TP Policy Document | Pricing based on Volumes …Activities
4. Pricing Catalogue | Customer-facing pricing catalogue aggregating component costs + margin — feeds fact-based conversations | Pricing Catalogue | Frame Agreements
5. Reporting Mechanism | Automated reporting of intercompany charges, subcontractor costs, margin by customer/product/group | TP Dashboard | Full transparency on costs and performance
6. Regulatory Compliance | Czech, Polish, Spanish, and JV-country tax authority compliance; OECD Transfer Pricing Guidelines | TP Documentation | Enterprise risk management